## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Project 5 (Twin Stick Survival Shooter [WIP]) |  |  |  |  | Jay Nimkar | Jnimka2@uic.edu
Week Of: April 14 - 20 |  |  |  |  | Jagjit Bhatia | jbhati3@uic.edu
[5 empty] | Nicholas Bezinovich | nbezin2@uic.edu
Group # 2 |  |  |  |  | Tigran Petrosyan | tpetro3@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Week After That | Issues
Prepare Sprint Sheet for Upcoming Week | 0 | All |  |  | Sprint sheet for week of 21-27 prepared | Update sprintsheet for next week
Decide upon project idea | 1 | Nicholas Bezinovich |  |  | Decided upon a top down, twin stick style, round survival game | Start fleshing out mechanics of game
Character Design | 3 | Tigran Petrosyan |  |  | (Medic, Heavy, Ranged, Frost Mage) | Flesh out Characters skills, strengths, flaws
Begin Design Documentation | 4 | Tigran Petrosyan |  |  | Create Document & push to github | Update Design Document
Learn Node.js | 5 | All |  |  | Go over tutorials & have basic understanding of language | Begin development
Decide upon frontend framework | 6 | Jagjit Bhatia |  |  | Begin Searching for framework | Show rest of group chosen framework
Lookup Game assets | 7 | Jay Nimkar |  |  | Begin searching for free game assets to use (character sprites & animations, enemy sprites & animations, backgrounds)
Design Server | 8 | Jay Nimkar |  |  | Basic functionality