## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project:
Week Of:
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
| 1 | Nicholas | refer to previous sprint sheet | design of communication protocol, server backend, start coding server | Testing
| 2 | Tigran | Design of character, uploaded documentation and sprint sheet, research on animation | operation codes (loading and running game), collision and sprites (client frontend and backend), updating documentation, frontend coding | Testing, documentation
| 3 | Jighat | refer to previous sprint sheet | design of server sockets and handlers in node.js, working on phasers, building lobby (client side), building main game mechanics, front end coding, finding game assets | Tesing and polishing the game, enhancing visual aspect of the game
| 4 | Jay | setup basic socket connections, downloaded express, testing http stuff, design API, communication side for objects | implement APIs, unit testing, networking part (running game on several machines), probably consolidate APIs | Testing
Final project documentation | 5 | All
THINGS BELOW THIS LINE ARE FROM AFTER THE PROJECT CHANGE TO UNO
Documentation | 6 | Tigran |  | New Documentation, UML Diagrams, Activity Diagrams
Server Programming | 7 | Jagjit |  | Server Side Op codes,
Client Programming | 8 | Nickolas |  | Lobby Screen, PlayerJoined Function
Client Programming | 9 | Jay |  | Main Game Screen, IP Address & Sockets
Testing | 10 | All |  | Testing & BugFixing