## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Project 5 (Twin Stick Survival Shooter [WIP]) |  |  |  |  | Jay Nimkar | Jnimka2@uic.edu
Week Of: April 29-May 4 |  |  |  |  | Jagjit Bhatia | jbhati3@uic.edu
[5 empty] | Nicholas Bezinovich | nbezin2@uic.edu
Group # 2 |  |  |  |  | Tigran Petrosyan | tpetro3@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Prepare Sprint Sheet for Upcoming Week | 0 | All | Sprint sheet for week of 21-27 prepared | Update sprintsheet for next week
Decide upon project idea | 1 | Nicholas Bezinovich | Decided upon a top down, twin stick style, round survival game | Start fleshing out mechanics of game
Character Design | 3 | Tigran Petrosyan | (Medic, Heavy, Ranged, Frost Mage) | Flesh out Characters skills, strengths, flaws
Begin Design Documentation | 4 | Tigran Petrosyan | Update Design Document | Create UML, FLOW, JSON Formatting Diagrams. Also Update Document
Learn Node.js | 5 | All | Go over tutorials & have basic understanding of language | Begin development
Decide upon frontend framework | 6 | Jagjit Bhatia | Begin Searching for framework | Show rest of group chosen framework
Lookup Game assets | 7 | Jay Nimkar | Begin searching for free game assets to use (character sprites & animations, enemy sprites & animations, backgrounds)
Design Server | 8 | Jay Nimkar | Basic functionality | Sockets & Flow
Client Operation (Exit_Game) | 9 | Jay Nimkar |  | Implement Op-Code
Client Operation (Class_Selected) | 10 | Nicholas Bezinovich |  | Implement Op-Code
Client Operation (Game_Loaded) | 11 | Jay Nimkar |  | Implement Op-Code
Server Operation (Player_Joined) | 12 | Jagjit Bhatia |  | Implement Op-Code
Server Operation (Player_Left) | 13 | Jagjit Bhatia |  | Implement Op-Code
Server Operation (Update_Selections) | 14 | Jagjit Bhatia |  | Implement Op-Code
Server Operation (Begin_Game() | 15 | Tigran Petrosyan |  | Implement Op-Code
Server Operation (Load_Game()) | 16 | Tigran Petrosyan |  | Implement Op-Code
JSON Format | 17 | All |  | Decide upon and finalize JSON formatting for client/server communication
Get Lobby Working | 18 | ALL |  | Implement Lobby from both frontent & Backend perspective | Implement Gameplay from both frontend & backend perspective